## JIRA Backlog Detailed
Title | Description | Story Points | Assigned To | Branch Name | Status
Title | Project Documentation SRS,Jira | 2 | Om Prakash | Feature/document-setup | Done
Title | Develop user registration module with form validation and secure password hashing. | 5 | Om Prakash | feature/auth-registration | To Do
Title | Develop user registration module with form validation and secure password hashing. | 5 | Om Prakash | feature/auth-login | To Do
Title | Implement role-based access with middleware validation and restricted admin routes. | 3 | Om prakash | feature/role-access-control | To Do
Title | Allow users to upload MP3, WAV, and M4A files with secure storage and validation. | 5 | Aditya | feature/audio-upload | To Do
Title | Implement browser-based microphone recording and auto-upload to backend. | 8 | Aditya | feature/live-recording | To Do
Title | Integrate Whisper model with Flask backend for speech-to-text conversion. | 8 | Aditya | feature/whisper-integration | To Do
Title | Add language selection and pass language parameter to transcription model. | 5 | Atul | feature/multilang-support | To Do
Title | Optimize transcription process to ensure <10 seconds processing time. | 8 | Atul | feature/performance-optimization | To Do
Title | Display generated transcript on user dashboard with proper formatting. | 5 | Atul | feature/display-transcript | To Do
Title | Enable transcript download in TXT and PDF formats. | 5 | Atul | feature/download-transcript | To Do
Title | Create dashboard to show user transcription history with pagination. | 8 | Naveel | feature/history-dashboard | To Do
Title | Develop admin panel to monitor users and transcription activities. | 5 | Navel | feature/admin-dashboard | To Do
Title | Create Users table schema with required fields. | 3 | Naveel | feature/db-users | Done
Title | Create Transcriptions table schema with required fields and relationships. | 3 | Utakarsh vashisht | feature/db-transcriptions | Done
Title | Implement bcrypt hashing and prevent plain text password storage. | 5 | Utakarsh vashisht | feature/password-security | To Do
Title | Implement file validation and prevent path traversal vulnerabilities. | 5 | Anas | feature/secure-file-handling | To Do
Title | Deploy application to cloud platform with environment configuration. | 8 | Anas | feature/cloud-deployment | To Do
Title | Configure GitHub integration with automated deployment pipeline. | 5 | wajheed | feature/ci-cd-setup | To Do
Title | Implement real-time streaming transcription functionality. | 13 | wajheed | feature/realtime-transcription | To Do
Title | Add speech-to-text translation capability as enhancement. | 8 | nishant | feature/translation-feature | To Do
Title | Presentation,final Report | 3 | nishant | feature/report | To Do